## Sheet1
Project Name: | Scheduling Simulation | Planned |  | Actual |  |  | % Completed
Milestone | Activity | Start Date | Duration | Start Date | End Date | Duration
Initial Phase | Project Initiation and Planning | 2020-05-12 | 7 days | 2020-05-12 | 2020-05-19 | 7 days
Process Plan | Scheduling Algorithms
Design | Software Design
Model Design
UI Design
Implementation | Coding
Integration
Testing | Unit Testing
Integration Testing
System Testing
Closure | Release
Documentation