## Sheet1
Project Name: | Scheduling Simulation | Planned |  | Actual |  |  | % Completed
Milestone | Activity | Start Date | Duration | Start Date | End Date | Duration
Initial Phase | Project Initiation and Planning | 2020-05-12 | 6 days | 2020-05-12 | 2020-05-18 | 6 days | 100
Design | Scheduling Algorithms | 2020-05-15 | 5 days | 2020-05-15 | 2020-05-18 | 3 days | 100
| Software Design | 2020-05-16 | 3 days | 2020-05-16 | 2020-05-18 | 2 days | 100
| Model Design | 2020-05-19 | 4 days | 2020-05-19 | 2020-05-23 | 4 days | 100
| UI Design | 2020-05-18 | 10 days | 2020-05-18 | 2020-06-01 | 13 days | 100
Implementation | Coding | 2020-05-21 | 25 days | 2020-05-21 |  |  | 50
| Integration | 2020-06-01 | 12 days | 2020-06-01 |  |  | 50
Testing | Unit Testing | 2020-05-19 | 25 days
| Integration Testing | 2020-06-01 | 12 days
| System Testing | 2020-06-12 | 5 days
Closure | Release | 2020-06-23 | 1 day
Documentation